Huntington High School

2024-25 Strategic Plan

Honorable Team-player Optimistic Well-rounded Nurturing

Goal 1

Achievement and Growth

Huntington High School's overall achievement results will raise by 5.6% to 57.26% proficiency in English and by 17.74% to 35.74% proficiency in Math by 2025 State Summative Testing.

Goal 2

Integrating Family and Community Engagement

By May 2025, HHS will improve family and community engagement by 8% to directly impact at least 300 families (18% of our population) during the 2024-25 school year, as evidenced by contact logs/attendance sheets.

Goal 3

Becoming a Model of Continuous Improvement

By May 2025, Huntington High School will improve family and community engagement by 8% to directly impact at least 300 families (18% of our population) during the 2024-25 school year, as evidenced by contact logs/attendance sheets.

Goal 1: Achievement and Growth

| Goal Title: Achievement and Growth ELA (English Language Arts) and Math Proficiency |  |
| --- | --- |
| Goal Description: Huntington High School's overall achievement results will raise by 5.6% to 57.26% proficiency in English and by 17.74% to 35.74% proficiency in Math by 2025 State Summative Testing. |  |
| Performance Measures: SAT, PSAT, KHAN, Bluebook and Common Formative Assessments |  |
| Strategy 1: Professional Learning Community (PLC) Data Meetings: Teachers will meet in PLC groups during morning meetings. These PLC meetings will have a collaborative structure, agenda will be focused on student achievement (data driven). |  |
| Action Step 1: |  |
| What action: | Students will take the PSAT in the fall, Full Practice SAT in December (coordinated by Math and English teachers), and a Full Practice SAT (Late February/Early March) |
| Who is responsible? | Math and English Teachers |
| When: | 8/06/2024 - 6/02/2025 |
| Evidence/Activity |  |
| Action Step 2 |  |
| What action: | Once a month, teachers will analyze results during Professional Learning Communities (PLCs) to determine common skill deficiencies and develop action plans for skill-based lessons to address learning loss. |
| Who is responsible? | Math Teachers, English Teachers and County Academic Specialist |
| When: | 8/06/2024 - 6/02/2025 |
| Evidence/Activity |  |
| Action Step 3 |  |
| What action: | Pacing guides will be developed and implemented by teachers with common core classes. |
| Who is responsible? | Core Teachers |
| When: | 8/06/2024 - 9/01/2024 |
| Evidence/Activity |  |
| Action Step 4 |  |
| What action: | Common Assessments will be developed and implemented by teachers with common core classes. |
| Who is responsible? | Core Teachers |
| When: | 8/06/2024 - 6/02/2025 |
| Evidence/Activity |  |
| Strategy 2: PSAT/SAT practice and school-wide programs, ALEKS, Achieve3000 Literacy, and Khan, will be used to address deficiencies and increase test scores. |  |
| Action Step 1 |  |
| What action: | To improve SAT and Lexile scores, students must complete six activities per month on Achieve3000 Literacy. |
| Who is responsible? | Language Arts and Social Studies, Science |
| When: | 8/06/2024 - 6/02/2025 |
| Evidence/Activity |  |
| Action Step 2: |  |
| What action: | Students in Algebra I, Algebra I Support, Algebra II and Geometry should spend 30 minutes or complete five topics weekly on ALEKs. Individual student goals will be set during one-on-one conferences after initial knowledge check. Teachers will utilize “Time & Topics” reports to track data and progress for all students. They will collaborate on strategies to address areas of weakness. |
| Who is responsible? | Math teachers |
| When: | 8/06/2024 - 6/02/2025 |
| Evidence/Activity |  |
| Action Step 3: |  |
| What action: | To improve SAT scores students will level up at least two activities per week in Khan for English. |
| Who is responsible? | Language Arts Teachers |
| When: | 8/06/2024 - 6/02/2025 |
| Evidence/Activity |  |
| Action Step 4: |  |
| What action: | To improve SAT scores students will level up at least two activities per week in Khan for Math. |
| Who is responsible? | Math Teachers |
| When: | 8/06/2024 - 6/02/2025 |
| Evidence/Activity |  |
| Action Step 5 |  |
| What action: | Math teachers will develop and provide a “SAT Boot Camp” for Juniors to provide math instruction based on student data, commonly missed questions on SAT, and lessons to address learning loss. |
| Who is responsible? | Math teachers, County Academic Specialist |
| When: | 8/06/2024 - 6/02/2025 |
| Evidence/Activity |  |
| Action Step 6 |  |
| What action: | Incentives will be provided for students during SAT prep for meeting set goals; including exemption from Finals if required scores are achieved in that specific area of study. |
| Who is responsible? | Math and ELA Teachers, Behavior Interventionist, Student Support |
| When: | 8/06/2024 - 6/02/2025 |
| Evidence/Activity |  |

| Strategy 3: Math, English, and Special Education Co-teachers will address learning loss through co-taught and small group instruction. |  |
| --- | --- |
| Action Step 1 |  |
| What action: | Co-teachers (both the regular education and the special education teachers) will work with small groups of students who score below proficiency to address learning loss and increase academic achievement. |
| Who is responsible? | Math, ELA and Special Education Co-teachers |
| When: | 8/06/2024 - 6/02/2025 |
| Evidence/Activity |  |
| Action Step 2 |  |
| What action: | Co-teachers will continually use Khan Academy and Achieve 3000 Literacy data to form small groups and check student progress. |
| Who is responsible? | Math, ELA and Special Education Co-teachers |
| When: | 8/06/2024 - 6/02/2025 |
| Evidence/Activity |  |

| Strategy 4: Additional resources and support will be provided for staff and students. |  |
| --- | --- |
| Action Step 1 |  |
| What action: | After-school tutoring will be provided to students voluntarily. Students struggling or failing in a particular class will be referred to tutoring sessions based on midterm and quarterly reports. Parent contact will be made for referred students. |
| Who is responsible? | Teachers, Students, Counselors |
| When: | 8/06/2024 - 6/02/2025 |
| Evidence/Activity |  |
| Action Step 2 |  |
| What action: | Back on Track and Recovery will be offered in order for students to recover failing grades and be in good standing to graduate. |
| Who is responsible? | Teachers, Counselors, Grad Coaches, Students |
| When: | 8/06/2024 - 6/02/2025 |
| Evidence/Activity |  |
| Action Step 3 |  |
| What action: | Additional resources will be provided upon request to promote literacy and numeracy across the curriculum. |
| Who is responsible? | Teachers, Joedy Cunningham |
| When: | 8/06/2024 - 6/02/2025 |
| Evidence/Activity |  |
| Action Step 4 |  |
| What action: | Additional support staff will be hired to meet the needs of the whole child. Support staff will include Attendance Specialist, Behavior Specialist, Counselor, Social Worker, Communities in Schools facilitator, Graduation Coach, Parent Partner, & a Social Worker at Crossroads Academy. |
| Who is responsible? | Joedy Cunningham |
| When: | 8/06/2024 - 6/02/2025 |
| Strategy 5: All teachers will use highly effective teaching practices. |  |
| Action Step 1 |  |
| What action: | Math teachers will be trained on Visible Learning for Mathematics Strategies |
| Who is responsible? | Math Teachers |
| When: | 8/06/2024 - 6/02/2025 |
| Evidence/Activity |  |
| Action Step 2 |  |
| What action: | Math teachers will implement Visible Learning Strategies in each classroom |
| Who is responsible? | Math Teachers |
| When: | 8/06/2024 - 6/02/2025 |
| Evidence/Activity |  |
| Action Step 3 |  |
| What action: | English teachers will implement Silent Sustained Reading (SSR) using Penny Kittle and Kelly Gallagher models. |
| Who is responsible? | English Teachers |
| When: | 8/06/2024 - 6/02/2025 |
| Action Step 4 |  |
| What action: | Practice SAT questions will be embedded in classes throughout the year. |
| Who is responsible? | Teachers |
| When: | 8/06/2024 - 6/02/2025 |
| Evidence/Activity |  |
| Action Step 5 |  |
| What action: | Develop an Instructional Framework template to meet the needs of all students. |
| Who is responsible? | Leadership and Administration |
| When: | 8/06/2024 |
| Evidence/Activity |  |
| Action Step 6 |  |
| What action: | Train staff and implement use of Instructional Framework. Integrate new expectations in lesson planning. |
| Who is responsible? | Leadership, Administration, and teachers |
| When: | 8/06/2024 - 6/02/2025 |
| Action Step 7 |  |  |
| What action: |  | A stipend will be offered to professional personnel to complete Apple Training and become a Certified Apple Teacher. |
| Who is responsible? |  | Joedy Cunningham |
| When: |  | 8/06/2024 - 6/02/2025 |

Goal 2: Integrating Family and Community Engagement

| Goal Title: Integrating Family and Community Engagement |  |  |
| --- | --- | --- |
| Goal Description: By May 2025, HHS will improve family and community engagement by 8% to directly impact at least 300 families (18% of our population) during the 2024-25 school year, as evidenced by contact logs/attendance sheets. |  |  |
| Performance Measures: Sign-In Sheets and Contact Logs |  |  |
| Strategy 1: Huntington High Student Support PLC will collaborate to create intentional family engagement events that help families support student learning. |  |  |
| Action Step 1 |  |  |
| What action: | Huntington High will host monthly Title I family engagement events. |  |
| Who is responsible? | Parent Partners |  |
| When: | Monthly |  |
| Evidence/Activity |  |  |
| Action Step 2 |  |  |
| What action: | Huntington High will hold a collaborative Resource Fair with feeder schools. |  |
| Who is responsible? | CIS Site Coordinator, Student Support, Support Staff from feeder schools, Parent Partner |  |
| When: | Fall 2024 |  |
| Evidence/Activity |  |  |
| Strategy 2: Huntington High will increase communication with the student body, families, and stakeholders. |  |
| Action Step 1: |  |
| What action: | HHS (Huntington High School) will produce a digital newsletter and a weekly callout sharing pertinent school information regarding events, opportunities, resources, and student celebrations. |
| Who is responsible: | Chris Hughes, Counseling Department, Joedy Cunningham, Amy Cunningham |
| When: | 8/06/2024 - 6/02/2025 |
| Evidence/Activity |  |
| Action Step 2: |  |
| What action: | HHS staff will frequently post events, opportunities, resources, and student celebrations on the school’s social media accounts and webpage |
| Who is responsible? | HHS Staff, Amy Nolte, Parent Partner, Amy Cunningham, Hilary Gibson |
| When: | Minimum of once a week |
| Evidence/Activity |  |
| Action Step 3: |  |
| What action: | HHS Student Support PLC will continue to update the digital pamphlet for families and students showcasing available courses, extra-curricular activities, and engagement opportunities. |
| Who is responsible? | Student Support PLC, Parent Partner |
| When: | 8/06/2024 - 6/02/2025 |
| Evidence/Activity |  |
| Action Step 4: |  |
| What action: | HHS will use television monitors in various hallways to update students on events, opportunities, resources, and student celebrations. |
| Who is responsible? | Chris Hughes, HHS Staff |
| When: | 8/06/2024 - 6/02/2025 |
| Evidence/Activity |  |

Goal 3: Becoming a Model of Continuous Improvement

| Goal Title: Becoming a Model of Continuous Improvement |  |  |  |
| --- | --- | --- | --- |
| Goal Description: Huntington High School will improve academic success through data-driven, evidence-based decision-making for structure implementation, evidenced by a 5% increase in attendance and a 5% increase in graduation rates. |  |  |  |
| Performance Measures: College Board Data, Khan Academy Data, Common Formative Assessments, Attendance Data, Walkthrough Data |  |  |  |
| Strategy 1: Huntington High will develop and implement a PLC schedule to address the needs of all students. |  |  |  |
| Action Step 1 |  |  |  |
| What action: | Freshman Academy will develop a schedule to include days for content planning, addressing attendance issues, PBIS (Positive Behavior Interventions and Supports) implementation, student interventions, student success, and grade level communication. |  |  |
| Who is responsible? | John Adkins, Freshman Academy |  |  |
| When: | 8/06/2024 - 6/02/2025 |  |  |
| Evidence/Activity |  |  |  |
| Action Step 2: |  |  |  |
| What action: | During PLCs teachers will analyze data and develop rigorous CFAs (Common Formative Assessments) for instructional planning to establish consistent grading methods and assessment protocols. This will allow teachers to find content gaps in student learning and differentiate as needed. |  |  |
| Who is responsible? | Administration and Department Chairs |  |  |
| When: | 8/06/2024 - 6/02/2025 |  |  |
| Evidence/Activity |  |  |  |
| Action Step 3 |  |  |  |
| What action: | Huntington High will create a Master Schedule that incorporates allotted time for PLCs for all content areas. |  |  |
| Who is responsible? | Joedy Cunningham |  |  |
| When: | 8/06/2024 - 6/02/2025 |  |  |
| Evidence/Activity |  |  |  |
| Action Step 4 |  |  |  |
| What action: | At the beginning of each month, during PLC time, monitoring teachers will review and update accommodation documentation logs. |  |  |
| Who is responsible? | Special Education Monitoring Teachers |  |  |
| When: | 8/06/2024 - 6/02/2025 |  |  |
| Evidence/Activity |  |  |  |
| Strategy 2: Huntington High School will implement PBIS with fidelity to increase a positive school culture, increase attendance, and promote expected behaviors. |  |  |  |
| Action Step 1 |  |  |  |
| What action: |  |  | Staff will be trained on positive behavior interventions and supports (PBIS); the why behind this framework. |
| Who is responsible? |  |  | Leadership, Administration, Student Support |
| When: |  |  | 8/06/2024 - 6/02/2025 |
| Evidence/Activity |  |  |  |
| Action Step 2 |  |  |  |
| What action: |  |  | Professional development will be provided on the PBIS plan and H-TOWN matrices throughout the year to reinforce its importance. |
| Who is responsible? |  |  | Leadership, Administration, Student Support |
| When: |  |  | 8/06/2024 - 6/02/2025 |
| Evidence/Activity |  |  |  |
| Action Step 3 |  |  |  |
| What action: |  |  | Professional development will be provided on how to implement the PBIS plan and matrices in all aspects of the day at Huntington High. |
| Who is responsible? |  |  | Leadership, Administration, Student Support |
| When: |  |  | 8/06/2024 - 6/02/2025 |
| Evidence/Activity |  |  |  |
| Action Step 4 |  |  |  |
| What action: |  |  | Staff will be expected to refer to the H-TOWN matrices when expectations are met or not met. At least 30 walk-throughs per week will be conducted and data shared with staff on the use of H-TOWN. |
| Who is responsible? |  |  | Administration |
| When: |  |  | 8/06/2024 - 6/02/2025 |
| Evidence/Activity |  |  |  |
| Action Step 5 |  |  |  |
| What action: |  | Using Sibme, coaching cycles will be provided to teachers to increase engagement and classroom management. |  |
| Who is responsible? |  | Administration and Behavior Interventionist |  |
| When: |  | 8/06/2024 - 6/02/2025 |  |
| Evidence/Activity |  |  |  |

| Action Step 6 |  |
| --- | --- |
| What action: | Monthly, the Leadership Team will review behavior data to identify trends. Action plans will be made and if needed training provided, during PLCs, to teachers on new/adjusted school-wide approaches to resolve and/or prevent current behavior issues. |
| Who is responsible? | Leadership Team and Administration |
| When: | 8/06/2024 - 6/02/2025 |
| Evidence/Activity |  |

| Strategy 3: Huntington High School will set and sustain high expectations to ensure rigorous instruction is aligned to improved outcomes, state standards, and teaching expectations during collaborative planning and all school environments. |  |
| --- | --- |
| Action Step 1 |  |
| What action: | ICLE (International Center for Leadership in Education) Consultant will focus on the coteaching model and engagement strategies to create and support an academic culture and collaboratively establish collective commitments that support the school's mission, vision, values and goals. |
| Who is responsible? | Administration, ICLE consultant, Teachers |
| When: | 8/06/2024 - 6/02/2025 |
| Evidence/Activity |  |
| Action Step 2: |  |
| What action: | Administration will complete a total of 30 instructional walkthroughs weekly. Administrators will provide feedback and conference with teachers regarding rigor, relevance, and student engagement. Student engagement data will be delivered to teachers bi-monthly through the staff newsletter. |
| Who is responsible? | Administration |
| When: | 8/06/2024 - 6/02/2025 |
| Evidence/Activity |  |
| Action Step 3: |  |
| What action: | Administration will monitor the effectiveness of co-teaching models in co-taught classes through classroom walk-throughs and observations to ensure quality of practice. |
| Who is responsible? | Administration, Teachers, Special Education Teachers |
| When: | 8/06/2024 - 6/02/2025 |
| Evidence/Activity |  |
| Action Step 4: |  |
| What action: | Based on walkthrough data and student achievement data, targeted professional development will be delivered to teachers during PLC’s and/or coaching cycles. |
| Who is responsible? | Administration, County Academic Specialists, ICLE Consultant, Behavior Interventionist |
| When: | 8/06/2024 - 6/02/2025 |
| Evidence/Activity |  |
| Action Step 5: |  |
| What action: | Professional development will be provided to teachers on the implementation of interventions/accommodations as they apply to SAT/IEP’s/504’s. |
| Who is responsible? | Special Education Teachers, Section 504 Coordinator and County Specialists |
| When: | 8/06/2024 - 6/02/2025 |
| Evidence/Activity |  |
| Action Step 6: |  |
| What action: | Administration will aim to decrease teacher turnover by developing a support system through mentorship. (NBCT (National Board-Certified Teacher) applicants, TIP (Teacher Induction Program) teachers, GROW teachers) |
| Who is responsible? | Teacher Mentors, NBCT Mentors, Academic Coach |
| When: | 8/06/2024 - 6/02/2025 |
| Evidence/Activity |  |
| Action Step 7: |  |
| What action: | HHS staff will evaluate data from various sources (culture/climate survey, leadership survey, family/community survey, achievement data, discipline and attendance data) to develop an overall assessment of existing systems and make recommendations for the next semester/school year. |
| Who is responsible? | Administrative Team, Leadership Team |
| When: | 8/06/2024 - 6/02/2025 |
| Evidence/Activity |  |

| Action Step 8: |  |
| --- | --- |
| What action: | Administration and the Special Education Department Chair will use a Service Verification Checklist to review five IEP files monthly. Files will be reviewed and if needed changes will be made to ensure we are complying. Once a semester administration will conduct a school wide Special Education audit using a compliance checklist to ensure IEP services are being met with 100% compliance. |
| Who is responsible? | Administrative Team, Special Education Dept. Chair |
| When: | 8/06/2024 - 6/02/2025 |
| Evidence/Activity |  |